## Sheet1
Project Name | Digital Training Management & Feedback Protal
Client | Flipkart
Created By | Name of the Product Owner / Client Name
Creation Date | 2025-06-16
Approval Date | 2025-06-20
Epic | User Story ID | Features / Title | User Story | Status | Acceptance Criteria
Launch the Digital Training Management & Feedback Portal,You can access Register for Trainings, Access Training Materials,Submit feedback & View Progress | D001 | Register | As a first time visitor to the DTM website, I want to register my account, so that I can login to the application | New | New user should be able to Register account with valid data
| D002 | Login | As a registered user, i want to login to the website so that i can see my account details etc. | New | System must validate user credentials and allow login if credentials are correct
| D003 | Trainings | As a registered user, I can access the training Module. It display all training informations | New | Users can accessthe Training Modules, with valid Login Credentials
| D004 | Access Training Materials | As a registered user, I can access the Training materials. | New | Users can access Training Materials
| D005 | Feedback Portal | As a user I can provide feedback for the trainings. | New | Users can prove feedback for specific trainings
| D006 | Logout | Use can access the “LogOut” | New | User can access “LogOut”
Create the Salesforce Object Setup, Tabls,etc | D007 | Object Setup | Create the Custom Object | New | Users can create custom Objects
| D008 | Tabs | Create the Tabs for Specific Custom Project | New | Users can create custom tabs
|  | Layouts | Create the Layouts from the specific Custom Object | New | User can create the layouts for the specific custom object
Develop an enterprise portal that manages the employee onboarding process, integrates with Salesforce CRM and automates functional testing using selenium. | D001 | Login
| D002 | Onboarding
| D003 | Asset Allocation
| D004 | Monitor Onboarding
| D005 | Functional Testing
| D006 | CRM Salesforce